## Instructions
Objective of this exercise:
To create a development plan to evenly distribute the implementation of the use cases over the Contruction Phase
To allocate use cases to each team member for equal work distribution and responsibility
Instructions:
1 | Save file immediately as <your team name> i.e. Team01
2 | Use the Development Schedule worksheet and populate this sheet with the use case numbers - list the use case names & numbers under the heading Use Case Glossary in Column A
3 | The dates indicate when you will have completed the implementation of the use case(s), this will be used for assessment purposes
4 | So if you say that A100 will be done by 7/8 August, we can then test that use case
5 | The data in columns B & N MUST NOT be changed - this is the same for all students and all groups
6 | When scheduling the use cases, try to do the critical ones first and the reports/queries last

## Development Schedule
Use Case Development Schedule 2019
Team Name: ABCD
|  |  |  | Progress Checks | Progress Checks | Progress Checks | Progress Checks | Progress Checks | Progress Checks | Progress Checks
Team Member | 30/31 Jul | 6/7 Aug | 13/14 Aug | 20/21 Aug | 27/28 Aug | 3/4 Sep | 10/11 Sep | 17/18 Sep | 1/2 Oct | 8/9 Oct | 15/16 Oct | 22/23 Oct | 2019-10-28
A | Database Implementation |  | A0300 |  | C0800 |  | B0600 | C1000 C1100 | B0200 |  |  |  | Project Due
B | [6 empty] | C0100 C0500 C0700 | C0200 |  | B0300 |  | C0400
C |  |  | A0200 A0400 |  | C0300 C0900 | [6 empty] | B0500
D |  |  | A0100 B0100 |  | B0700 B0800 |  |  |  | C0600 |  | B0400
Use Case Glossary
A0100: Login
A0200: Logout
A0300: View Account Details
A0400: Edit Details
B0100: Register
B0200: Join Challenge
B0300: Record Steps
B0400: View Progress
B0500: Compare Progress
B0600: Search
B0700: Join Group
B0800: Create Group
C0100: Add Challenge
C0200: View Challenges
C0300: View Milestones
C0400: End Challenge
C0500: Add Journey
C0600: Update Challenge
C0700: View Journeys
C0800: Add Milestone
C0900: Remove Milestone
C1000: Update Journey
C1100: Remove Journey