## Instructions
Objective of this exercise:
To create a development plan to evenly distribute the implementation of the use cases over the Contruction Phase
To allocate use cases to each team member for equal work distribution and responsibility
Instructions:
3 | The dates indicate when you will have completed the implementation of the use case(s), this will be used for assessment purposes
4 | So if you say that A100 will be done by 7/8 August, we can then test that use case

## Development Schedule
Use Case Development Schedule 2019
Team Name: CBA
Progress Checks
Team Member | 30/31 Jul | 6/7 Aug | 13/14 Aug | 20/21 Aug | 27/28 Aug | 3/4 Sep | 10/11 Sep | 17/18 Sep | 1/2 Oct | 8/9 Oct | 15/16 Oct | 22/23 Oct | 2019-10-28
C | Database Implementation |  | B0100 - Add Module | A0200 - Post Listing |  |  |  | B0101 - Prompt Lecturer to Prescribe Textbook | B0300 - Prompt Lecturer to Update Textbook |  | C0100 - Prescribe Textbook |  | Project Due
B |  |  | A0100 - Register | B0200 - Remove User |  | A0301 - Rate User |  |  | A0302 - Report User |  | A0300 - Search User
A |  |  | A0101 - Log In |  |  | A0201 - Update Listing |  |  | A0202 - Delete Listing |  | A0400 - Search Listing
Use Case Glossary
Use Case ID
A0100 - Register
A0301 - Rate User
A0302 - Report User
B0200 - Remove User
A0300 - Search User
B0100 - Add Module
B0101 - Prompt Lecturer to Prescribe Textbook
B0300 - Prompt Lecturer to Update Textbook
C0100 - Prescribe Textbook
A0200 - Post Listing
A0101 - Log In
A0201 - Update Listing
A0202 - Delete Listing
A0400 - Search Listing